## User Stories
Team: 33 (The OmegaNerds)
ID | Name | As a/an | I want to… | so that… | Notes | Priority | Effort/ Cost (Story points) | Business value | Dependencies (which stories must be done prior to this) | Status (not started, in progress, done) | Acceptence Test1 | Acceptence Test2
1 | Enter Coins | Customer | Be able to enter coins | I can recieve a product back |  | 5 | 3 | Must | 2 | Done | Given that the correct amount is entered for the item that the user picks when they enter coins they will recieve the item. | Given that the incorrect amount is entered when the user picks an item then they will not recieve the item.
2 | Select Product | Customer | Enter a letter then number | I can pick an item |  | 1 | 2 | Must | N/A | Done | Given that the sequence is correct, when the user enters a position then the item price and name will show. | Given that the sequence is incorrect, when the user enters a position, then the input will not register.
3 | Receive change | Customer | Enter a large amount of coins ie greater than price of item | I can receive change |  | 7 | 5 | Must | 1 | Done | Given that the total amount of coins entered is greater than the item price, wne the user enters the last coin, the change will be dispensed. | Given that the total amount of coins entered is less than the item price, when the user enters a coin, the price will deduct by amount entered.
4 | Cancel Purchase | Customer | Be able to retrieve entered coins i.e cancel | I can receive coins back |  | 8 | 3 | Must | 1 | Done | Given that the coins entered does not exceed the item price, when the cancel button is pressed, then the coins entered will be returned to the user. | Given that the coins entered exceeds the item price, when the cancel button is pressed, then a message will be displayed to inform that the process cannot be cancelled.
5 | Out of Stock | Customer | be able to be notified when an item is out of stock | I can recieve the money entered back |  | 3 | 5 | Must | 2 | Done | Given that the item is not in stock when the user enters the item they want then the machine will say item unavailable and give them their coins back. | Given that the item is in stock when the user enters their item then they recieve the item.
6 | Coin Validation | Customer | be able to be notified when a coin is not vaild | I can receive the coin back |  | 6 | 1 | Must | 1 | Done | Given that the coins entered is not accepted the user will be given their invalid coin(s) back. | Given that the coins entered are accepted the user is not given their coins back.
7 | Change Notification | Customer | be able to be notified when there is no change available | I can be notifed |  | 2 | 2 | Must | N/A | Done | Given that the coin dispenser is empty, when the user enters an item position, then display a message to inform them there is no change remaining. | Given that the coin despenser is not empty, when the user enters an item position, then the item name and price will be displayed.
8 | Price Information | Customer | be able to be notified of the price and name of a selected item | I can enter the correct amount of coins |  | 4 | 2 | Must | 2 | Done | Given that the user selects an item when they use the machine they then can see the price and name of the item and so enter the right amount of coins. | Given that the item is out of stock, when the user enters their desired item, then the user will be notified that the item is out of stock.
9 | Coin Removal | Owner | be able to get coins out of the vending machine | I can retrieve profits from the machine |  | 13 | 0.5 | Must | 12 | Done | Given that the owner is the one opening the machine when they enter a key or code then they can recieve the money from the machine money holder. | Given that the owner is not the one opening the machine when entering an invalid coi or key then the machine coin holder will not open.
10 | Coin Topup | Owner | to be able to top up the change in the machine | the customer can recieve correct change back |  | 14 | 0.5 | Must | 12 | Done | Given that the owner is the one opening the machine, when they enter a key or code, then they can open the coin dispenser to fill it. | Given that the owner is not the one opening the machine, when they enter an invalid key or code, then they cannot open the coin dispenser to fill it.
11 | Change Product Price | Restocker | to be able select an item in the machine | I can change the price of an item |  | 15 | 3 | Must | 12 | Done | Given that the restocker is the one opening the machine, when they enter a key or code, then they can change the price of an item at a position. | Given that the restocker is not the one opening the machine, when they enter an invalid key or code, then they cannot change the price of an item at a position.
12 | Restock Options | Restocker | be able to enter a restock key | I can use restock options |  | 11 | 1 | Must | N/A | Done | Given that the correct key is in the machine, when the user trys to use a restock option, then the user can proceed to the desired task, e.g. restock or retreive money. | Given that the correct key has not been used, when the user trys to enter restock options, then they will not be permitted access.
13 | Fully Restock | Restocker | tell the machine that it has been fully restocked | it can know how many items are present |  | 16 | 1 | Must | 12 | Done | Given that the machine has been refilled when the restocker has entered the products then the machine knows the products are instock and can function properly. | Given that the machine has not been refilled when the user has entered the restocking mode, then the user can exit the restocking mode with no change.
14 | Fault | Customer | to be able to recieve a product from the machine after a fault | I can receive the product |  | 10 | 3 | Must | 18 | To be started | Given that the product hasn't passed through the sensor in the bottom collector when the customer has entered thier coins then the machine will run the command to send the item again. | Given that the machine has not faulted and the item passed through the sensor when the customer requests the item then the machine will not send another.
15 | Receiver Top Up Dispenser | Owner | the machine to topup the change collection tubes from the reciever | the customer can recieve correct change back |  | 17 | 2 | Must | 1 | Done | Given that the change tubes levels are low when the customer is entering their coins then the machine will topup the associating tube. | Given that the change tubes are full when the customer is entering thier coins then the machine will send the money to the money collection for the owner.
16 | Power Off | Owner | turn the power off | when I turn the power on again all the data has saved |  | 18 | 1 | Must | N/A | Done | Given that the data has been saved to an external file, when the user removes power from the machine and then resupplies with power, then the machine will retain item names, prices and stock. | Given that the power has not been removed from the machine, when an item is purchased, then total profit, stock etc will be saved to an external file.
17 | Temperature | Owner | Be able to regulate temperature | I can improve food & beverages quality i.e. beverages are better cold |  | 19 | 3 | Must | 12 | Done | Given that the user is using the restock key, when they acess the temperature option, then they can change the temperature that the machine is at. | Given that the user is accessing the restock options for temperature, when they try to lower or raise the temperature above a certain value, then the user will be notified via a warning
18 | Receive Item | Customer | extend the machine arm | receive the product |  | 9 | 2 | Must | 3 | Done | Given that the correct number of coins has been entered into the machine, when the user receives their change, then the machine arm will extend to release the product. | Given that thein correct number of coins has been entered into the machine, when the user finishes entering coins, then the machine arm will not extend to release the product.
19 | Enter Notes | Customer | be able to enter notes into the machine | I can pay for a product |  | 20 | 1 | Must | 31 | To be started | Given that the user has entered a large note when they enter a correct note then the system will give them the correct change back. | Given that the user has entered a incorrect note when they enter a note then the machine will give back the note and not release a product or give back change
20 | To use a card | Customer | be able to use a card | I can pay for a product |  | 21 | 1 | Must | 31 | To be started | Given that the user has used a valid card when they go to pay with their card then the machine will give them the item | Given that the user has given an invalid card when they go to pay for an item then the machine will not give an item and say the card is invalid
21 | To use a phone based payment | Customer | be able to use a phone with a card on it | I can pay for a product |  | 22 | 1 | Must | 31 | To be started | Given that the user has given a correct card on their mobile device when they go to pay for thier item then the mcahine will sotre the cash and give the item to the user | Given that the user has an invalid card on thier phone or insuffiecent amount of money on the card when the user goes to pay then the machine will either give and error with an invalid card or say the the account has insufffiecent funds
22 | Loyalty/ Staff Card | Customer | be able to use a loyalty card/voucher | I can pay for a product |  | 23 | 1 | Must | 31 | To be started | Given that the user has a valid loyalty/staff card when they go to pay for their item then the mcahine will subtract the amount from the loyalty card and give the user their item. | Given that the user has not got a valid loyalty card when they got to may then they will have to pay for it normally
23 | Alternate Curriencies | Customer | be able to enter different currencies such as euro or dollars | I can pay for a product |  | 24 | 1 | Must | 30 | To be started | Given that the user has entered valid foriegn currency when they go to pay then the machine will calculate the the price of the product and give back accurate change | Given that the user has entered invalid coins or notes in a foriegn currency when they go to pay then the machine will give back the cash and give an error message
24 | PIN Confirmation | Owner | be able to enter a pin code to confirm identity | I can access the owner menu |  | 25 | 1 | Must | 32 | To be started | Given that the owner is swapping to the owner menu when the machine swaps to the menu it will ask for a PIN then if correct the machine will go to the owner menus | Given that it is not the owner swapping to the owner menu when the user is entering an incorrect PIN then the mcahine will not swap to the menu and stay in the customer instance
25 | Password Confirmation | Owner | be able to enter a password to confirm identity | I can access the owner menu |  | 26 | 1 | Must | 32 | To be started | Given that the owner is swapping to the owner menu when the machine swaps to the menu it will ask for a password then if correct the machine will go to the owner menus | Given that it is not the owner swapping to the owner menu when the user is entering an incorrect password then the mcahine will not swap to the menu and stay in the customer instance
26 | Biometrics Confirmation | Owner | be able to use my finger/face to confirm identity | I can access the owner menu |  | 27 | 1 | Must | 32 | To be started | Given that the owner is trying to enter the owner menus when the machine attempts to swap to the menu it will ask for either a fingerprint or face ID then if the owner is validated then the owner will gain acces to the menus | Given that it is not the owner trying to accesss the machine when the machine asks for the biometric ID then if incorrect will stay in the customer menus
27 | GPS location | Owner | be able to receive the GPS location of the machine | I can tell where the machine is |  | 28 | 2 | Must | N/A | To be started | Given that the machine is connected to the internet when the owner goes to access the location of the machine then the server will give the machines location | Given that the machine is not connected to the internet or the server whne the owner tries to get the location of the machine then the owner will not recieve the location
28 | Item type | Customer/Owner | be able to see the type of product I have selected eg sweets/chocolate | have more information about a product |  | 29 | 2 | Must | N/A | To be started | Given that the owner or customer has asked for the type of the product when the machine atempts to check the type then it will return the type | Given that the user has not asked for the type of product then the machine will not return the type
29 | Transaction Logs | Owner | be able to see all transactions from the machine in a csv file | have more information about the machine such as date/time, value, vending machine ID… |  | 30 | 5 | Must | N/A | To be started | Given that the a purchase of a product has been made when the machine gives out the change then the machine will log the purchase to the server including the all transaction information
30 | Currency Type | Owner | be able to change currency type of machine | so that I can use different currencies |  | 31 | 2 | Must | N/A | To be started | Given that the user follows the instructions when the user requests to change currency type then the machine will change to the desired type
31 | Payment Type | Owner | be able to add payment types to the machine | so that I can pay by different methods |  | 32 | 2 | Must | N/A | To be started | Given that the user follows the instructions when the user requests to add a payment tpye then the machine will add the desired type
32 | Verification methods | Owner | be able to add verifcation methods to the machine | so that I can verify who the person is in different ways |  | 33 | 2 | Must | N/A | To be started | Given that the user follows the instructions when the user requests to add a verification method then the machine will add the desired type
33 | Machine Setup | Owner | be able to set up a machine | so that I can make transactions |  | 34 | 5 | Must | N/A | To be started | Given that the machine is not set up, when the user trys to set up the machine, the system will provide instructions for the user
Note on K3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Add date of start and end